## HL
[23 empty] | SEISS coms & eligibility checker | [9 empty] | SEISS | BANK HOL | [10 empty] | SSP
 | time axis 2020-04-06 to 2020-06-19
1 | C-19 Business Account & Basic SEISS | bar: 2020-04-06
Analysis | bar: 2020-04-06 to 2020-04-09; 2020-04-14
Design | bar: 2020-04-06 to 2020-04-09; 2020-04-14
| Governance | 2020-04-14: DWP, Fact Check & C3
Build | bar: 2020-04-14 to 2020-04-17; 2020-04-20 to 2020-04-21
Test | bar: 2020-04-21 to 2020-04-23
Private Beta (23/04) | bar: 2020-04-23
Public Beta (27/04) | bar: 2020-04-27
2 | C-19 Self Employed | bar: 2020-04-06
Analysis | bar: 2020-04-15 to 2020-04-17
Design | bar: 2020-04-17; 2020-04-20 to 2020-04-23
| Governance & signoffs | 2020-04-24: DWP; 2020-04-28: Fact Check; 2020-04-30: C3
Nuance Implementation | bar: 2020-04-29 to 2020-05-01
Nuance Test | bar: 2020-05-04
Private Beta (12/05) | bar: 2020-05-05
Public Beta (14/05) | bar: 2020-05-06
3 & 4 | C-19 Employed & Unemployed | bar: 2020-04-06
Analysis | bar: 2020-04-22 to 2020-04-24
Design | bar: 2020-04-24; 2020-04-27 to 2020-04-30
| Governance & signoffs | 2020-05-01: DWP; 2020-05-05: Fact Check; 2020-05-07: C3
Nuance Implementation | bar: 2020-05-05 to 2020-05-07; 2020-05-11 to 2020-05-12
Nuance Test | bar: 2020-05-13 to 2020-05-14
Private Beta (12/05) | bar: 2020-05-15
Public Beta (14/05) | bar: 2020-05-19; 2020-05-21
5 | Tax Credits | bar: 2020-04-06
Kick-off | bar: 2020-04-27
| Research & Analysis | 2020-05-04: Playback; 2020-05-11: Playback
Design | bar: 2020-05-04 to 2020-05-07; 2020-05-11 to 2020-05-15; 2020-05-18 to 2020-05-22
Customer Testing | bar: 2020-05-12; 2020-05-19
| Governance | 2020-05-11: DWP; 2020-05-13: Fact check / C3; 2020-05-18: Sign-offs
Web Build | bar: 2020-05-25 to 2020-05-29
AB test design | bar: 2020-05-28 to 2020-05-29; 2020-06-01
Nuance Implementation | bar: 2020-05-25 to 2020-05-29
Nuance Test | bar: 2020-06-01 to 2020-06-03
Private Beta (09/06) | bar: 2020-06-04
Public Beta (11/06) | bar: 2020-06-09
Note on X10: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Live with Basic SEISS infromation

## Business Account (hidden)
|  |  | 2020-04-06 | 2020-04-07 | 2020-04-08 | 2020-04-09 | 2020-04-10 | 2020-04-11 | 2020-04-12 | 2020-04-13 | 2020-04-14 | 2020-04-15 | 2020-04-16 | 2020-04-17 | 2020-04-18 | 2020-04-19 | 2020-04-20 | 2020-04-21 | 2020-04-22 | 2020-04-23 | 2020-04-24 | 2020-04-25 | 2020-04-26 | 2020-04-27 | 2020-04-28 | 2020-04-29 | 2020-04-30 | 2020-05-01 | 2020-05-02 | 2020-05-03 | 2020-05-04 | 2020-05-05 | 2020-05-06 | 2020-05-07 | 2020-05-08 | 2020-05-09 | 2020-05-10
Analysis & insight | Owner | Status
Requirements gathering | Cristina Dunare | Complete | bar: 2020-04-14
Data gathering | Nick Mitchell | Ongoing | bar: 2020-04-14
Top queries by channel | Nick Mitchell | In progress | bar: 2020-04-14
Customer language | Nick Mitchell | In progress | bar: 2020-04-14
Create DEP backlog (interstitial & tagging / data passes) | Nick Mitchell | bar: 2020-04-14
Backlog refinement | Nick Mitchell | bar: 2020-04-15
Design | Owner | Status
Business Account: Conversation nodes / shell | Louise Jones | Complete | bar: 2020-04-06 to 2020-04-09
Business Account: Conversation copy | Louise Jones | Under DWP review | bar: 2020-04-06 to 2020-04-09; 2020-04-14 to 2020-04-15
Business Account: Direct answers | Louise Jones | In progress | bar: 2020-04-09; 2020-04-14 to 2020-04-15
SEISS: Intro copy and direct answers | Dave Ord / Louise Jones | bar: 2020-04-15
Interstitial page design & copy | Louise Jones | In progress
Dialogue strategy | Louise Jones | In progress | bar: 2020-04-14 to 2020-04-15
Self Employed
Employed
Unemployed
Governance | Owner | Status
Business Account: Conversation copy sign-off (DWP, Fact check) | Louise Jones | bar: 2020-04-17
Business Account: Conversation copy sign-off (C3) | Tom Maddox | bar: 2020-04-17
Interstitial page sign-off (DWP, Fact check) | Louise Jones | bar: 2020-04-17
Interstitial page sign-off (C3) | Tom Maddox | bar: 2020-04-17
Dialogue strategy sign-off | Tory & Martin | bar: 2020-04-16
Security review | Steven J Hall / Martyn Clements
SDA&I review (Solution Design Architecture & Innovation) | Joe Leask
Build
VA Nuance Technical Design | David Hammond | Complete | bar: 2020-04-14 to 2020-04-17; 2020-04-20 to 2020-04-21
VA Nuance Content Implementation | Rachel Pratt | bar: 2020-04-14 to 2020-04-17; 2020-04-20 to 2020-04-21
VA Nuance NDEP Dev | bar: 2020-04-17; 2020-04-20
Interstitial DEP | Tim Gorringe
Interstitial DEP datapass & tagging | Tim Gorringe
BTA / PTA tagging | TBC
SEISS tagging | Nick Wilson
Test
VA Nuance QA | bar: 2020-04-21 to 2020-04-22
Interstitial DEP | TBC
E2E / Private Beta | Martin, Tory, Cristina, Dave O, Tom Maddox | bar: 2020-04-23
Private Beta
CAB (Change Advisory Board) | EPS (Enterprise Platform Services) |  | 2020-04-22: TBC if needed
Go live VA | bar: 2020-04-23
Go live interstitial | bar: 2020-04-23
Public Beta
Private Beta sign-off | CAB assigned Digital serv manager & Martin Bloore | bar: 2020-04-27

## Actions (hidden)
Action | Owner | Due date
Create different opening copy and bypass user type questions in VA, when user is coming from SEISS journey | Louise Jones
Include SEISS content in the social questions, as direct questions | Louise Jones
Share Ask Ruth data & analysis | Mark Marvin | 2020-04-16
Speak with Isabelle, James and Phil on getting additional content design support for C-19 for Louise | Tory | 2020-04-15
Speak with Tory to close down design decisions on having 1 or 2 PTA / BTA interstitial pages, and how the customer journey should flow | Rachel R | 2020-04-15
Action | Owner | Due date
Content design and sign-off milestones, and Nuance implementation, dev and test timelines for hitting 6/05 Self Employed Public Beta |  | 2020-04-22
Investigate if Louise can get Visio |  | 2020-04-22
Share Self Employed content documentation with Rachel P (Q&As, Direct Questions), including highlighting common questions across SE and Employed journeys |  | 2020-04-23
Andy, Gill & Louise to define approach to dividing up remaining 2 C-19 content design and Tax Credits redesign workstreams |  | 2020-04-23
Arrange Tax Credits 'kick-off' |  | 2020-04-24
Reach out to Michael to collaborate on VA and webchat design patterns |  | 2020-04-22

## Qs & RAIDs (hidden)
Question | Comments | Due date

## R&R (hidden)
Design | Andy / Louise
Nuance build
DEP build
Nuance Test
DEP test
Governance | Andy / Louise
Delivery against plan | Cristina

## Questions (hidden)
Same shell for Business v SE
SEISS intro & social / direct Q
Content changes
Content sign off
Additional Qs from Mark Marvin
Help with content creation
Help with sign off
Fact check - Tory & James Low
SE
JRS
SSP
VAT defferals
Datapass / tagging (requirements & who will develop) | Jon